**ToWe Project – Project Management Record of Activities**

|  |  |
| --- | --- |
| Project: | **2015-1-UK01-KA201-013431** |
| Institution: | **Kingston University** |
| Period: | **November 2016 – February 2017** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Dates** | **Name** | **Activity** | **Cost if Appropriate** |
| 2.11.16 | Helen Sutherland | Emails to partners |  |
| 5.11.16 | Helen Sutherland | Emails to partners  Phoned KU finance department – Denis Leahy |  |
| 7.11.16 | Helen Sutherland | Interim Report and EU platform |  |
| 7.11.16 | Helen Sutherland and Yasmin Mukadam | Interim Report |  |
| 14.11.16 | Helen Sutherland | Financial Reports and EU platform  Emails to partners |  |
| 15.11.16 | Helen Sutherland | Emails to Finance |  |
| 15.11.16 | Helen Sutherland and Denis Leahy | Financial reporting meeting |  |
| 15.11.16 | Helen Sutherland | Financial Reports checks |  |
| 21.11.16 | Helen Sutherland and Yasmin Mukadam | Interim report, Financial Reports checks and EU platform |  |
| 5.12.16 | Helen Sutherland and Yasmin Mukadam | Preparation for the transnational meeting 3 |  |
| 21.12.17 | Helen Sutherland and Yasmin Mukadam | Preparation for the transnational meeting 3 |  |
| 3.1.17 | Helen Sutherland | Impact Exercise from Conference |  |
| 4.1.17 | Helen Sutherland | Preparation for the transnational meeting 3  Emails re: funding payment |  |
| 6.1.17 | Helen Sutherland and Alison McGee | Meeting with Setting Partner - Achieving for Children |  |
| 6.1.17 | Helen Sutherland | Working on EECERA proposal for dissemination |  |
| 11.1.17 | Helen Sutherland | Responding to emails to Sandnes Kommune re transnational meeting |  |
| 11.1.17 | Helen Sutherland and Yasmin Mukadam | Preparation for the transnational meeting 3 |  |
| 24-27.1.17 | Helen Sutherland and Yasmin Mukadam | Transnational Meeting 3 |  |
| 9.2.17 | Helen Sutherland | Marketing leaflet for M1 |  |
| 13.2.17 | Helen Sutherland | Financial reporting 3B  Certificates of Attendance for M3  Email to partners |  |
| 13.2.17 | Helen Sutherland and Yasmin Mukadam | Minutes, impact exercise and time line for the transnational meeting 3  Email to partners |  |
| 14.2.17 | Helen Sutherland | Financial reporting 3B  M3 minutes  Email to partners |  |
| 15.2.17 | Helen Sutherland | M3 minutes  Email to partners |  |
| 16.2.17 | Helen Sutherland | QA questionnaires for EEL group setting visits and reflective session  QA questionnaire for job shadowing  Job shadowing programme template |  |
| 20.2.17 | Helen Sutherland | Project management of paperwork and electronic folders |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Date | 28.2.17 | Signature (project manager) | H:\Helen's Signature.PNG |
| Date |  | Signature (employer) |  |